## Stakeholder Register
Name | Role | Department | Interest | Influence | Expectations | Communication Frequency
Marcus Lee | HR Representative | Human Resources | High | Medium | Reduced ticket load on HR; smooth adoption without disrupting existing HR processes | Bi-weekly check-in
Ben Okafor | IT Support Lead | Information Technology | High | Low | Reduced onboarding-related ticket volume; clear technical integration requirements up front | Weekly during build/test
Priya Anand | Design Team Lead | Product/Design | Medium | Low | Clear requirements before design work starts; minimal rework from late-stage scope changes | Weekly during design phase
Elena Vasquez | AI Tool / API Owner | IT Platform Engineering | High | Medium | Clear API/integration requirements; assistant's tool access stays within agreed scope | Weekly during configure/build
Sofia Marin | Change Management Lead | HR / Organizational Development | High | Medium | Smooth adoption; effective training rollout; resistance managed proactively | Weekly during rollout
Angela Torres | Training Team Lead | Learning & Development | Medium | Low | Enough lead time to prepare training materials; clarity on what the assistant will and won't do | Bi-weekly
Gok | AI Project Manager | PMO | High | High | Successful pilot delivery; stakeholder alignment across HR, IT, and Design | Daily / ongoing
Raj Patel | Organization Head | Executive Leadership | Medium | High | Project stays aligned to strategic goals; visible progress without needing day-to-day involvement | Monthly steering review
David Whitfield | Funding Partner | Executive / Finance | Low | High | Budget stays on track; clear go/no-go decision points before further funding is released | At each funding gate
Nadia Farouk | Sponsor / Executive | Executive Leadership | Medium | High | Measurable ROI; project reflects well in front of leadership; minimal organizational risk | Monthly steering review
Dev Team (Collective) | Development Team | Engineering | High | Low | Clear, stable requirements before build starts; realistic timeline for configuration and testing | Daily during build/test
(Represents new hires collectively) | New Employee (End User) | N/A — all departments | High | Low | Fast, accurate answers to onboarding questions; doesn't want to feel unsupported or handed to a bot with no human option | Continuous, via the assistant itself