# Business Case

## Tech Bridge Solutions — Agentic AI Employee Onboarding Platform

## 1. Executive Summary

New hire onboarding at TechBridge Solutions is a manual, email-driven process that depends heavily on direct back-and-forth between new hires and HR/IT staff. This creates a high volume of repetitive tickets, slows onboarding down to roughly three weeks, and places the entire process on the shoulders of a small number of HR staff who must manually reference policies, org charts, and handbooks for every question.

This business case proposes building an Agentic AI Onboarding Assistant: a tool that can autonomously answer routine HR/IT questions, guide new hires through standard onboarding steps, and escalate only the exceptions — high-risk, ambiguous, or policy-sensitive requests — to a human.

Design target: a 30% reduction in manual HR/IT onboarding effort and ticket volume within 3 months of deployment, freeing an estimated 10% of HR capacity per month for higher-value work. The recommended solution can be designed, built, and piloted at moderate cost, using existing tools and API-based AI services rather than new headcount or major capital investment.

This is a design target for a fictional pilot, not a measured outcome — used here to demonstrate business case methodology.

## 2. Problem Statement

Onboarding new employees currently takes about three weeks and relies on manual, email-based coordination between new hires and HR/IT. Without a self-service channel for routine questions, new hires must email HR directly for even simple requests — equipment, system access, policy clarifications — and HR must personally respond to each one.

This creates two compounding problems: new hires experience uncertainty and anxiety while waiting on replies, and HR falls further behind as onboarding volume grows, since every new hire adds the same repetitive question load to an already stretched team.

## 3. Current State, Ideal State & Gap

3.1 Current State — The onboarding process takes approximately 3 weeks per new hire and is handled through manual email exchanges between new hires and HR. There is no shared, always-available resource that can answer routine onboarding questions on its own.

3.2 Ideal State — An agentic AI system handles the majority of routine onboarding questions and tasks automatically, reducing manual effort and turnaround time while increasing HR/IT productivity. New hires get faster answers and experience less uncertainty during their first weeks.

3.3 Gap — The gap between current and ideal state is defined, as a design target, as a 30% reduction in manual onboarding effort and ticket volume, achieved within 3 months of go-live.

3.4 Root Cause Analysis — Working backward from the symptom to the underlying cause:

- Symptom: HR receives a high volume of tickets during onboarding.

- Why: New hires don't get fast replies to routine questions, so they follow up repeatedly or open new tickets.

- Why: HR is managing a growing volume of manual, repetitive work with limited capacity.

- Why: Onboarding support concentrates on a small number of HR staff — effectively a one-person effort per cohort.

- Why: That effort depends on manually referencing company policies, organizational structure, and paper-based or static handbooks for every question.

- Root cause: There is no shared, real-time knowledge and service layer between HR, IT, and new hires — every question requires a human to manually look up and relay an answer.

## 4. Options Considered

| Option | Pros | Cons |
| --- | --- | --- |
| 1. Expand HR headcount | Immediate added capacity; familiar hiring/training model | Highest ongoing cost; slow to hire and train; doesn't fix the underlying lack of a shared knowledge layer |
| 2. Static self-service tools (FAQ pages, forms) | Lower cost than headcount; some ticket deflection | Can't handle nuanced or multi-step questions; still requires manual upkeep as policies change |
| 3. Agentic AI onboarding assistant (recommended) | Handles nuanced, multi-step questions; escalates only high-risk/ambiguous cases to humans; scales without added headcount | Requires upfront design and governance guardrails; needs change management and training for HR/IT |

Recommendation: Option 3 is recommended. It addresses the root cause directly rather than treating the symptom, and it is projected to cost less on an ongoing basis than expanding HR headcount while delivering a better new hire experience than static self-service tools.

## 5. Cost Analysis

Design-stage estimate, expressed as relative tiers rather than fixed dollar figures until scoping is finalized:

| Cost Category | Estimated Tier | Notes |
| --- | --- | --- |
| Design & build (labor/time) | Moderate | Primarily internal time investment for workflow design, prompt/agent configuration, and testing — no new hires required |
| AI tool / API usage | Low | Pay-as-you-go API calls; low upfront investment, cost scales with usage volume |
| Change management & training | Low | Short HR/IT training sessions plus updated documentation; no dedicated training budget assumed |

Overall: this can be designed and piloted at a moderate total cost, weighted toward time investment rather than capital or new headcount spend.

## 6. Benefits

| Tangible | Intangible |
| --- | --- |
| Design target: 30% reduction in onboarding tickets within 3 months | Reduced HR workload stress |
| Design target: ~10% freed HR capacity per month | Stronger organizational knowledge retention and consistency across onboarding cohorts |
| Increased HR/IT productivity on higher-value work | Higher new hire satisfaction |
| Shorter effective onboarding cycle time | Reduced new hire anxiety in the first weeks |

## 7. ROI & Assumptions

7.1 Assumptions Supporting ROI

- Reducing manual, repetitive onboarding tasks will directly increase HR and IT productivity.

- A 30% reduction in onboarding-related tickets is achievable within the first 3 months of deployment (design target, to be validated against a pilot cohort).

- HR and IT stakeholders will treat supporting this initiative as a priority alongside their regular day-to-day responsibilities.

7.2 Assumption Constraints — This business case is scoped as a grassroots, low-footprint pilot rather than a funded enterprise program:

- No formal approval from senior/executive leadership has been sought at this stage.

- No dedicated budget has been allocated; costs are limited to time and low-cost API usage.

- The solution must operate within existing IT access and security controls — no new elevated permissions.

- Human–AI interaction is required for exceptions; the assistant is not a full replacement for HR judgment.

- Design must remain human-centric: the assistant supports HR/IT staff and new hires, not replaces the HR relationship.

- This project is positioned as an AI flagship / pilot initiative to demonstrate agentic AI value before wider investment is requested.